## Sheet1
MICT - Pallet Link Merge
Task | Description | Days
1 | Create the configuration tables into the database. | 1
2 | Implementation of the Pallet Link functions into a Web API. | 10
3 | Changes to MICT user graphic interface. | 2
4 | Changes to MICT source code to consume the Pallet Link Web API. | 5
5 | Create a configuration screen for the MICT system. | 3
6 | Test and debug. | 3
7 | UAT. | 5
8 | Release to production environment. | 1
30