## Sheet1
SAPvsMES Reporting
Task | Description | Days
1 | Prepare staging environment | 1
2 | Analisis | 2
3 | Design | 2
5 | Implementation | 3
6 | Test and debug | 2
7 | Fix bugs | 2
8 | UAT | 2
9 | Release to production environment | 1
15
Breakdown
1 | Prepare the staging environment to build and test the solution before to implement into production environment. | 1
2 | Analisis (Check the source code en databases to identify changes to the MESvsSAP database, changes or creation of tables, store procedures, jobs etc.) | 2
3 | Design and implementation for Tesla customer (This should be transparent but is considered for a possible changes or corrections). | 1
4 | Desing and implementation for the customer selection (Database and source code). | 3
5 | Sinchronize the MESvsSAP database jobs with the BackFlush process. | 1
6 | Test and debug (Tesla) | 1
7 | Fix bugs | 1
8 | Test and debug (JDES) | 1
9 | Fix bugs | 1
10 | UAT | 2
11 | Release to production environment. | 1
15